{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["分解表（定稿）","Sheet3"],"not_rendered":{"external_links":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"分解表（定稿）","index":0,"n_rows":17,"n_cols":7,"rows_kept":17,"merged":[[0,0,0,6]],"flags":["formulas_cached_only"]}
["（二）2017年征兵工作任务分解"]
["序号","主 要 任 务","责任单位","责任领导","协作单位","完成时限","备 注"]
[1,"运用学生会做好征兵宣传工作，负责宣传现场的引导工作。","团委","王晖慧","学工处、各学院党总支","1月-6月"]
[2,"督办各学院对征兵工作落实；收集应征入伍学生学费补偿材料并报送","学工处","邝家旺",null,"4月-6月、9月-11月"]
[3,"按时报送相关数据，制定征兵方案。","武装部","覃业亮",null,"3月下旬"]
[4,"落实网上及现场应征报名","各学院党总支","各学院党总支书记",null,"4月10日-5月31日"]
[5,"调整完成征兵工作领导小组，根椐上级部门的安排和要求，结合我校实际，运用多种手段，在校园内营造好征兵氛围。                                      ","武装部","覃业亮","宣传部","4月底"]
[6,"组织报名的学生参加体检。","武装部","覃业亮","各学院党总支","5月底"]
[7,"组织应征学生完成复检、政治考核\n","武装部","覃业亮","各学院党总支","6月中旬"]
[8,"依椐兵役机关安排组织学生按时完成预征兵协议签订","武装部","覃业亮",null,"6月20日前"]
[9,"发布兵役登记通告，明确兵役登记的时间、对象、方法及有关事项。","武装部","覃业亮","各学院党总支","4月底"]
[10,"组织学生开展网上兵役登记。","各学院党总支","各学院党总支书记",null,"6月底"]
[11,"完成后续大学生报名、体检、政治考核等工作。","武装部","覃业亮","各学院党总支","8月底"]
[12,"预征学生的跟踪管理和持续发动。","武装部","覃业亮",null,"8月底"]
[13,"负责入伍学生的学籍管理服务，包括办理保留学籍、复学、转专业、考试资格审查等。","教务处","谢协驹","高职院","9月-12月"]
[14,"负责办理入伍学生的学费代偿、补偿及监管征兵专项经费使用等","计财处","李伟",null,"3月-12月"]
[15,"落实大学生入伍政策措施第9条之规定，考试升学加分。","研究生院","牟忠林",null,"按招录计划时间"]

{"sheet":"Sheet3","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}